## Master Audit
FIINNY.COM — Full Site Audit & Improvement Sheet
Live site audit ¦ Code review ¦ AI/SEO visibility ¦ Look & Feel ¦ April 2026
# | Category | Page / Area | Severity | Finding / Issue | Impact | Fix / Recommendation | Effort | Priority
1 | 🐛 Bug | Home — Hero | CRITICAL | 'Next' video section uses .mp4 files with broken href — clicking video thumbnails does nothing (href is a filepath, not embedded) | Users see feature cards but cannot watch demos — key conversion content is dead | Embed actual videos using <video> tags or YouTube iframes. Don't use raw anchor tags for video playback | Low | P0
2 | 🐛 Bug | Download Page | CRITICAL | Both App Store and Play Store buttons use href='#' — they go nowhere | Primary conversion point for mobile acquisition is completely broken | App Store: link to apps.apple.com/in/app/fiinny…/id6751309482. Play Store: link to play.google.com/store/apps/details?id=com.KaranArjunTechnologies.lifemap | Low | P0
3 | 🐛 Bug | All Pages | CRITICAL | Static export (output: 'export' in next.config.ts) kills all server-side API routes — Fiinny Brain chat returns 404 in production | AI chat feature is completely non-functional in the deployed site | Remove output: 'export'. Deploy on Vercel or Firebase App Hosting with SSR. Or move Fiinny Brain to client-side Gemini API call | Medium | P0
4 | 🐛 Bug | Contact Page | CRITICAL | Contact page uses a completely different navbar (simple border-b) vs every other page (floating island style) | Users feel they've navigated to a different product — major trust break | Replace ContactNavbar with the shared <Navbar /> component. Takes 5 minutes | Low | P0
5 | 🐛 Bug | layout.tsx | HIGH | Schema.org JSON-LD has fake phone '+91-9999999999' as contactPoint telephone | Google's Rich Results tool flags fake numbers — hurts trust signals and structured data validity | Replace with real support number or remove the telephone field entirely | Low | P1
6 | 🐛 Bug | Sitemap | HIGH | sitemap.ts only lists 3 URLs ('/', '/blog', '/login'). 19+ pages like /about, /trust, /pricing, /how-it-works, /careers, /contact, /download are missing | All those pages are invisible to Google and Bing — zero organic traffic to them | Add all static routes to sitemap.ts. Also add /tax, /changelog, /privacy, /terms, /countries | Low | P1
7 | 🐛 Bug | Blog Page | HIGH | Blog page renders empty — no posts visible. The Firebase Firestore fetch appears to fail silently in static export mode | Blog = zero content = zero SEO value. A page with just a headline and no articles ranks nowhere | Fix static export issue (see P0) OR pre-seed blog with at least 10 articles via Firebase. Add a loading/empty state | Medium | P1
8 | 🐛 Bug | Trust Page | MEDIUM | 'View Audit Summary (PDF)' link is href='#' — the TAC Security audit PDF is not linked | Major credibility claim with no evidence — sophisticated users will notice and distrust | Either upload the real PDF to /public/ and link it, or remove the link until it's ready | Low | P2
9 | 🐛 Bug | Tax Page | MEDIUM | Tax Autopilot has PAN + DOB form but no loading state, no error state, and no result UI visible in the fetched HTML | Users submit PAN and see nothing — or an infinite spinner — with no feedback | Add proper loading spinner, error messages, and a clear 'results' view. Use react-hook-form for validation | Medium | P2
10 | 🐛 Bug | All Pages | MEDIUM | No per-page <title> or <description> metadata on any page except the root layout — every page shows same generic title in Google tabs and search results | 'Fiinny - The Secure…' shows for every page. Google de-dupes identical meta → pages compete with each other | Export metadata const from each page.tsx. Unique title + description per page | Low | P1
11 | 🎨 Design | Home — Hero | HIGH | Hero headline is inconsistent with what the live site shows vs codebase — 'Financial clarity, automated.' vs 'Total Financial Control.' in code. The hero text animation (TypewriterText) is not visible in rendered output | Confusing brand voice. Typewriter effect is a premium touch that isn't working in prod | Fix typewriter text render. Settle on ONE hero headline — 'Financial clarity, automated.' is stronger | Low | P1
12 | 🎨 Design | Home | HIGH | Feature section is duplicated — 'Everything you need. All in one place.' section appears TWICE on the homepage with slightly different content | Looks unpolished and lazy. Visitors lose trust when they see repeated blocks | Remove the first (shorter) feature section. Keep only the second full-featured version with Tax Autopilot card | Low | P0
13 | 🎨 Design | Home — Footer | HIGH | Footer uses an 'F' letter avatar for the logo instead of the actual logo_icon.png image used everywhere else | Brand inconsistency — looks like a placeholder that was forgotten | Replace the F div with <Image src='/assets/images/logo_icon.png' />. 10 minute fix | Low | P1
14 | 🎨 Design | All Pages | MEDIUM | No dark mode support on any marketing/public page even though ThemeProvider and CSS variables are fully wired in the codebase | ~35% of users prefer dark mode. Missing it feels unfinished for a 'modern' fintech product | Apply dark: class variants to public page backgrounds and text. CSS variables already exist — just use them | Medium | P2
15 | 🎨 Design | Home — Social Proof | MEDIUM | Testimonials use placeholder initials (A, S, R) with no photos, no real review platforms linked, no review count or star aggregation shown | Fake-looking social proof can hurt credibility more than no social proof | Add Product Hunt badge, real App Store rating widget, or Google Play star count. Make testimonials feel verifiable | Medium | P2
16 | 🎨 Design | About Page | MEDIUM | About page has no team section, no founder photo, no LinkedIn links, no company story. Just a wall of text principles | For a fintech app asking for financial data access, anonymity erodes trust | Add 'Meet the Team' section with at least founder name + photo + LinkedIn. Builds massive trust for financial products | Medium | P2
17 | 🎨 Design | How It Works | MEDIUM | How It Works page is extremely sparse — 3 steps with 1-line descriptions. No screenshots, no animation, no feature depth | Does not explain the actual product. Users leave without understanding why Fiinny is different | Add per-step app screenshots, animated GIFs, or a short screen recording for each step | High | P2
18 | 🎨 Design | Careers Page | LOW | Careers page has job listings with no apply button/action — clicking apply does nothing | Cannot hire. Enthusiastic candidates bounce immediately | Add mailto: apply links or embed a Typeform/Google Form per job listing | Low | P2
19 | 🎨 Design | Home | LOW | 'What's coming next' section uses random stock video placeholders (Boy's Happy Ball Adventure, Video Generation…) as feature preview cards | Placeholder content in production looks unfinished and damages credibility | Replace with real screen recording snippets of the Fiinny app UI or use static mockup images instead | Low | P1
20 | 🔍 SEO | Sitemap | CRITICAL | Google, Bing, and AI web crawlers (GPTBot, ClaudeBot, Google-Extended) can only index what's in your sitemap + what they can crawl. With 19 pages missing from sitemap, those pages get zero AI training data attribution | Fiinny will not appear in AI answers for questions those pages should rank for | Add all pages to sitemap. Submit sitemap.xml to Google Search Console AND Bing Webmaster Tools | Low | P0
21 | 🔍 SEO | robots.ts | HIGH | robots.ts only disallows /admin/ and /api/ — this is fine. But there is no explicit 'Allow' for GPTBot, ClaudeBot, or Google-Extended AI crawlers | AI training crawlers may be missed in consolidated crawl budgets. Explicit allow signals help | Add specific rules for GPTBot, ClaudeBot, and Google-Extended to robots.txt to signal you WANT AI indexing | Low | P1
22 | 🔍 SEO | All Pages | HIGH | Zero blog content indexed. Blog = the #1 source of long-tail SEO and the primary way AI models (GPT, Claude, Gemini) learn about a product via web search | Fiinny does not show up when users ask AI assistants 'best expense tracker India' — there's no content to cite | Publish minimum 20 SEO articles: 'best expense tracker for India 2026', 'how to file ITR free India', 'split bills app India', 'SMS expense tracking India', etc. | High | P0
23 | 🔍 SEO | layout.tsx | HIGH | Schema.org markup uses priceCurrency: 'USD' but Fiinny is an Indian product priced in INR | Wrong currency in structured data confuses Google's understanding of your product category | Change priceCurrency to 'INR'. Add 'applicationCategory': 'FinanceApplication' and 'offers.price': '0' | Low | P1
24 | 🔍 SEO | All Pages | MEDIUM | Open Graph (og:) and Twitter Card meta tags are missing across all pages — no og:image, og:description, twitter:card | When someone shares fiinny.com on WhatsApp/Twitter/LinkedIn it shows no preview card — kills social sharing virality | Add og:title, og:description, og:image (1200x630 Fiinny branded card), and twitter:card to layout.tsx metadata | Low | P1
25 | 🔍 SEO | All Pages | MEDIUM | No canonical URL tags — duplicate content risk if pages are accessible via www. and non-www. versions | Google may split ranking signals between versions, halving SEO power | Add canonical: { url: 'https://fiinny.com/page' } in each page's metadata export | Low | P2
26 | 🔍 SEO | All Pages | MEDIUM | Page load performance: @mlc-ai/web-llm and @xenova/transformers are in dependencies and likely bundled — these are 100MB+ libraries | Slow initial JS load → poor Core Web Vitals → Google penalizes ranking. Also Safari may crash on mobile | Lazy-load these only when the AI feature is actively used. Use dynamic import() with loading boundaries | High | P1
27 | 🔍 SEO | Trust | MEDIUM | Trust page mentions 'ISO 27001 Aligned' and 'TAC Security' audit but has no structured data (LocalBusiness, Certification schema) to help AI/search understand Fiinny's security credentials | AI assistants citing 'most secure expense trackers' won't cite Fiinny — no machine-readable trust signals | Add SecurityAudit and Certification schema.org markup on the trust page | Low | P2
28 | 🚀 Feature | Pricing Page | CRITICAL | All 3 pricing plan CTAs route to /login — there is no actual payment flow. payments.ts Firebase function exists but is not wired to the frontend | Revenue = ₹0. The product has paying-tier plans advertised but no way to pay | Integrate Razorpay (easiest for India). Add checkout → Firestore subscription status → dashboard gate | High | P0
29 | 🚀 Feature | Dashboard | HIGH | Dashboard has no error boundary — a single Firestore failure on loadDashboardData crashes the entire 947-line component with a blank white screen | Any Firebase outage = complete product outage for all users. No fallback, no retry button | Add <ErrorBoundary> around dashboard. Show a 'Retry' card on fetch failure. Split into smaller components | Medium | P1
30 | 🚀 Feature | Dashboard | HIGH | No PIN/biometric app lock on web dashboard after session timeout — financial data visible to anyone who opens the tab | Fintech security standard requires re-authentication for sensitive data. Competitor apps (CRED, Fi) all have this | Add a PIN lock overlay after 15 min inactivity using Web Crypto API. 'Enter PIN to continue' modal | Medium | P1
31 | 🚀 Feature | All | MEDIUM | No referral / invite system despite a /dashboard/sharing route existing | Without viral loops, growth depends entirely on paid ads. Fintech CAC is high | Add 'Invite a friend → both get 1 month Premium'. Track via Firestore referral codes. High ROI growth lever | Medium | P2
32 | 🚀 Feature | Home | MEDIUM | No live user count / traction proof shown anywhere ('Join X users…' in CTA is placeholder text with no real number) | Without social proof numbers, the 'Join thousands' claim feels hollow and unverifiable | Connect a real-time Firestore user count to the CTA. Even '2,400 users' is better than 'thousands' | Low | P2
33 | 🚀 Feature | Analytics | MEDIUM | No product analytics (PostHog, Mixpanel, or GA4) on the marketing site — no way to know where users drop off in the conversion funnel | Cannot optimize what you cannot measure. Landing → sign up funnel is a black box | Add PostHog (free, privacy-friendly, works with Next.js). 1-hour setup. Start tracking today | Low | P1
34 | 🤖 AI Visibility | Global | CRITICAL | Fiinny has no Wikipedia page, no Crunchbase profile, no ProductHunt listing, no G2 listing — AI models (GPT-4o, Gemini, Claude) primarily learn about products from these authoritative sources | Zero chance of appearing in AI-generated lists of 'best expense tracker apps in India' since there is no authoritative reference for AI crawlers to cite | Create: 1) ProductHunt launch, 2) Crunchbase company page, 3) G2 listing with user reviews, 4) AngelList profile. These are free and are crawled by all AI training datasets | Low | P0
35 | 🤖 AI Visibility | Blog | HIGH | No content targeting AI-searched questions — queries like 'best free expense tracker India 2026', 'how to track UPI transactions automatically', 'SMS based expense tracker' return zero Fiinny results | When users ask GPT or Gemini for expense app recommendations, Fiinny is not in the training data or live search index | Write 20+ SEO blog articles targeting these long-tail queries. AI models use web search for recent recommendations — content is the only lever | High | P0
36 | 🤖 AI Visibility | Structured Data | HIGH | No FAQ schema on landing page or How It Works — AI models love FAQ markup for featured snippets and direct answers | Competitors with FAQ schema appear in AI Overviews in Google. Fiinny does not | Add FAQPage schema on homepage answering: 'Is Fiinny free?', 'Does Fiinny read my OTPs?', 'How does SMS tracking work?', 'Is Fiinny available on iOS?' | Low | P1
37 | 🤖 AI Visibility | PR & Links | MEDIUM | No press coverage, no backlinks from tech/fintech media (Inc42, YourStory, Economic Times, Mint, TechCrunch India) | Domain authority = 0-10 range. AI models weigh authority when citing sources. Low authority = never cited | Pitch story to Inc42 and YourStory about Fiinny's privacy-first approach and Tax Autopilot feature. One article = 100s of backlinks | Low | P1
38 | 🤖 AI Visibility | Social | MEDIUM | No active Twitter/X presence found. Instagram (@fiinnyapp) and LinkedIn are listed but posting frequency is unknown | Social signals inform AI recency. Zero activity = AI treats Fiinny as dormant/dead product | Post 3x per week minimum. Twitter: developer insights, privacy tips. LinkedIn: product updates, fundraising | Low | P2

## Look & Feel Changes
FIINNY — Look & Feel Improvement Plan
Visual design, UX consistency, and brand polish recommendations based on live site review
# | Page / Component | Current State | Problem | Recommended Change | Reference / Inspiration | Effort
1 | Homepage Hero | Split floating island nav + typewriter headline + hero carousel | TypewriterText component not rendering in prod; hero carousel has no phone frame/device mockup around it — images float without context | Add a phone frame (CSS border-radius + bezel) around hero carousel images. Fix TypewriterText by using a plain CSS animation fallback | Linear.app, Notion.so hero sections | Low
2 | Homepage — Duplicate Section | 'Everything you need. All in one place.' block appears twice | Users scrolling see identical section twice — feels like a copy-paste mistake | Delete the first (shorter) feature grid. Keep only the rich second block that includes Tax Autopilot | N/A | Low
3 | Homepage — Video 'Coming Soon' | 3 feature preview cards with placeholder stock videos | 'Boy's Happy Ball Adventure.mp4' as a feature preview is embarrassing in production | Replace with screen recordings of actual Fiinny UI, or static app screenshots with a 'Coming Soon' overlay | Raycast feature previews, Loom homepage | Low
4 | Homepage — Comparison | Chaos vs Fiinny table is duplicated (appears twice) | Same content duplication issue — second pass through identical comparison table | Remove the first comparison section or make one a condensed pill version and one the full table | N/A | Low
5 | Homepage — Testimonials | 3 initials-only avatars (A, S, R) with no verification | Looks placeholder. Fintech users are skeptical — unverified testimonials have near-zero persuasion value | Swap to: App Store / Play Store review embeds OR add photo + verified tag + date. At minimum show star count from stores | Notion, Linear social proof sections | Medium
6 | Homepage — CTA | 'Join thousands of users…' with no real number | Vague claim. Savvy users dismiss it immediately | Replace with a real live counter from Firestore. Even 1,200 is credible. 'Join 1,200+ users managing ₹X crore' | Stripe, Razorpay signup page CTAs | Low
7 | Homepage — Footer | 'F' letter block used as logo | Placeholder look. Every other page uses actual logo_icon.png | Replace F block with actual logo image. Add Instagram + LinkedIn icons with real links | N/A | Low
8 | Trust Page | Floating nav is different from rest of site (Home, Security, Help links) | Trust page uses its own custom nav — different brand feel | Use the shared Navbar component. Trust page especially needs to feel like part of the same product | N/A | Low
9 | Trust Page | 'glass-shield.png' and 'local-processor.png' images return 404 (not in public folder) | Broken image slots on a page that's supposed to convey reliability — catastrophic for trust | Add the missing PNG assets to /public/, or replace with high-quality SVG illustrations rendered in code | N/A | Low
10 | Trust Page — Audit Badge | 'TAC Security' badge with no real PDF link | 'View Audit Summary (PDF)' goes to href='#'. Breaks the entire claim | Either upload real PDF or remove button. Consider a 'Report Coming Q3 2026' if it's pending | N/A | Low
11 | About Page | Text-only page with no visuals, no team, no founder photo | For a finance product, anonymity = distrust. Users want to know WHO is handling their data | Add: founder card with name + photo + LinkedIn. Timeline of company milestones. 'Built in Hyderabad' map pin | Stripe, Wise About pages | Medium
12 | How It Works | 3 steps with 1-line descriptions only. No screenshots, no animation | Page feels like a draft. Doesn't explain what makes Fiinny different from Google Sheets | Add per-step phone screenshot + 1 animated GIF or Lottie showing the auto-parse flow in action | Notion How It Works, Splitwise walkthrough | High
13 | Pricing Page | All CTAs go to /login, no payment flow | Users who want to pay have no way to do so. Kills revenue | Add Razorpay payment links. Show 'Most Popular' badge more prominently. Add 'Save 37%' pill on yearly toggle | Notion, Linear pricing pages | High
14 | Download Page | Two empty cards with href='#' for App Store and Play Store | Zero downloads from website. A user who wants the app gives up | Link to actual store URLs. Add QR code. Add device mockup screenshots from actual app. Show star rating | Notion mobile download page | Low
15 | Blog Page | Empty page — just headline, zero articles | Blog = SEO engine + AI visibility. Empty blog = invisible website | Write and publish minimum 10 articles. Add category filters, estimated read time, featured image per post | Ghost.org blog design pattern | High
16 | Careers Page | Job listings with no apply action | Cannot recruit. No form, no email, nothing happens on click | Add mailto: links or Typeform embeds per job. Mark remote positions clearly. Add 'We're a team of N' line | Linear Careers page | Low
17 | Contact Page | Different navbar style (border-b) vs all other pages (floating island) | Visual inconsistency breaks brand cohesion at a high-trust page | Replace with shared <Navbar /> component. Unify footer style to match rest of site | N/A | Low
18 | All Pages — Dark Mode | No dark mode despite ThemeProvider existing | 35% of users use dark mode. Missing it feels unfinished in 2026 | Enable dark: variants on public page backgrounds and text. ThemeProvider + CSS variables are already wired | N/A | Medium
19 | All Pages — Favicon | Icon.png used as favicon but no Apple touch icon, no PWA manifest linked correctly | Poor experience on iOS homescreen add. No branded startup screen | Add manifest.json to /public/ (already referenced in metadata). Add apple-touch-icon 180x180 PNG | N/A | Low
20 | All Pages — Animations | Framer Motion animations are excellent but TypewriterText and some FloatingFeatureStack effects break in static export | Polished animations degrade to no-animation in prod — losing a premium feel | Fix static export issue (see Master Audit). Or add SSR-safe CSS animation fallbacks | N/A | Medium

## AI & SEO Visibility
FIINNY — AI Discoverability & SEO Playbook
How to make Fiinny visible to GPT, Gemini, Claude, Copilot, Perplexity, and Google AI Overviews
# | Action | Why It Works | How To | Timeline | Cost
1 | Fix sitemap.xml to include all 22+ pages | AI crawlers (GPTBot, ClaudeBot, Google-Extended) follow sitemaps. Missing pages = never indexed | Add all routes to sitemap.ts. Submit to Google Search Console and Bing Webmaster Tools | Week 1 | Free
2 | Add GPTBot + ClaudeBot to robots.txt as explicitly allowed | Signals to AI training crawlers that you WANT to be indexed and cited | Add: User-agent: GPTBot Allow: / and same for ClaudeBot, Google-Extended, PerplexityBot | Week 1 | Free
3 | Create Crunchbase company profile | Crunchbase is a primary source for AI models to learn about startups. GPT and Gemini cite it constantly | Go to crunchbase.com → Add Company → Fill all fields including description, location, founding date | Week 1 | Free
4 | Launch on Product Hunt | Product Hunt is in AI training data and crawled by all AI models. A successful launch = instant authority | Schedule a Product Hunt launch. Engage the community. Aim for Top 5 of the day | Week 2-3 | Free
5 | Create G2 profile and collect 10 reviews | G2 is the most cited SaaS review site in AI model outputs for product recommendations | Register at g2.com/products. Ask your existing users to leave reviews. 10+ reviews unlocks category ranking | Week 2-4 | Free
6 | Publish 20+ SEO blog articles targeting Indian fintech queries | AI models use web search when answering recent questions — your blog articles get cited as sources | Target: 'best expense tracker India 2026', 'UPI expense tracking app', 'SMS bank tracking app', 'split bills India app', 'how to file ITR free India', 'income tax regime calculator 2026' | Month 1-2 | ₹0 if in-house
7 | Add FAQPage schema.org markup to homepage | Google AI Overviews and featured snippets pull directly from FAQ schema. Highest ROI structured data change | Add FAQPage JSON-LD with 8-10 Q&As: Is Fiinny free? Does it read OTPs? How does SMS tracking work? Available on iOS? | Week 1 | Free
8 | Add HowTo schema.org markup to How It Works page | HowTo schema triggers rich results in Google — step-by-step cards appear in search. Also used by AI for 'how to track expenses India' | Wrap the 3-step process in HowTo schema with each step name and description | Week 1 | Free
9 | Fix Schema.org pricing currency (USD → INR) | AI models use structured data to understand product pricing. Wrong currency confuses categorization | In layout.tsx schema, change priceCurrency from 'USD' to 'INR' | Day 1 | Free
10 | Add Open Graph + Twitter Card meta to all pages | When content is shared on social media with rich previews, engagement goes up 3-5x. Shared content gets more backlinks → higher AI citation probability | Add og:title, og:description, og:image (1200x630 Fiinny card), twitter:card:summary_large_image to every page's metadata | Week 1 | Free
11 | Get press coverage from Inc42 or YourStory | AI models are trained on news articles. One Inc42 article about Fiinny = permanent citation source across GPT, Gemini, Claude | Pitch the Tax Autopilot feature as an exclusive story to Inc42. Frame as 'Hyderabad startup building India's first privacy-first ITR automation' | Month 1 | Free
12 | List on AngelList / Wellfound | AngelList is crawled by all AI models and cited for startup information. Also helps with talent visibility | Create company page at wellfound.com. Complete all fields. | Week 1 | Free
13 | Post consistently on Twitter/X with #fintech #India hashtags | Twitter is indexed by Bing and used by Perplexity AI as a real-time source. Consistent posting builds topical authority | 3 posts/week: product updates, privacy tips, fintech news commentary. Use @fiinnyapp handle | Ongoing | Free
14 | Create a public API documentation page | Technical users and AI models both use API docs as reference. Shows product maturity | Even if API is private, having a /docs page with overview improves crawlability and authority signals | Month 2 | Free
15 | Add canonical URLs to all pages | Prevents Google from splitting ranking signals between www/non-www versions | Add canonical: { url: 'https://fiinny.com/page' } in each page.tsx metadata export | Week 1 | Free
16 | Add website to every Indian startup directory | Directories like startupindia.gov.in, nasscom.in, trak.in all feed into AI training data | Register on: Startup India, NASSCOM, Tracxn (free tier), Crunchbase, CB Insights | Week 2 | Free

## Sprint Plan
FIINNY — 90-Day Fix & Growth Sprint Plan
Sprint | Focus | Tasks (in order) | Owner Hint | Done When
Week 1 — P0 Fixes | Critical bugs that break the product | 1. Remove output:'export' from next.config.ts → redeploy on Vercel/Firebase App Hosting 2. Fix Download page App Store + Play Store links 3. Fix duplicate sections on homepage (2× feature grid, 2× comparison table) 4. Fix Contact page nav → use shared Navbar 5. Fix sitemap.ts → add all 22 pages 6. Fix schema.org phone number and currency (USD→INR) 7. Add FAQPage + HowTo structured data to homepage | Frontend Dev | 0 broken links, sitemap has 22+ URLs, schema validates in Google Rich Results Test
Week 2 — SEO Foundation | Get indexed by Google, Bing, AI crawlers | 1. Submit sitemap.xml to Google Search Console 2. Submit sitemap.xml to Bing Webmaster Tools 3. Add per-page metadata (title + description) to all 22 pages 4. Add Open Graph + Twitter Card tags to all pages 5. Add canonical URLs 6. Add GPTBot, ClaudeBot, PerplexityBot to robots.txt as allowed 7. Create Crunchbase + AngelList profiles 8. List on Product Hunt (schedule launch for week 3) | Dev + Founder | All pages have unique meta. Google Search Console shows pages indexed.
Week 3 — Content Push | Blog articles = SEO + AI citation engine | 1. Publish 5 blog articles targeting India fintech keywords 2. Product Hunt launch 3. Pitch Inc42 / YourStory with Tax Autopilot story 4. Start Twitter/X posting cadence (3×/week) 5. Ask existing users for G2 reviews (target 10+) 6. Register on Startup India + NASSCOM directory | Founder + Content Writer | 5 articles live. Product Hunt launched. Social profiles active.
Week 4-6 — Payment Flow | Monetize the premium tiers | 1. Integrate Razorpay into Premium + Pro plan CTAs 2. Connect payment success → Firestore subscription status update 3. Gate premium features behind subscription check 4. Send payment confirmation email via Firebase 5. Add cancellation flow | Backend Dev | Users can actually pay and upgrade. Revenue > ₹0.
Week 6-8 — Trust & Design Polish | Make the site feel top-class fintech | 1. Add team section to About page (founder photo + LinkedIn) 2. Fix Trust page broken images (glass-shield.png, local-processor.png) 3. Link real TAC Security audit PDF or remove the button 4. Replace placeholder video cards with real app screenshots/GIFs 5. Replace 'F' letter logo in footer with real logo_icon.png 6. Add phone device frame around hero carousel 7. Fix Careers page Apply buttons (add mailto: or Typeform) | Designer + Dev | About page has real team. Trust page has 0 broken images. Careers page has working apply flow.
Week 8-12 — Growth Features | Viral loops + analytics | 1. Add PostHog analytics to marketing site 2. Build referral system (invite → 1 month Premium free) 3. Add live user counter to CTA section (pull from Firestore) 4. Add dark mode to all public pages 5. Add PIN lock overlay to web dashboard (15 min timeout) 6. Publish 15 more blog articles (total 20+) | Full Stack Dev | PostHog tracking active. Referral link generates real upgrades. Dashboard has PIN lock.